## Dummy Planner Extract
Task number | Outline number | Priority | Sprint | Name | Definition of done | Bucket | Assigned to | Resolution or NFA Date | Status | Stakeholder - Org Unit | Content Manager ID | External Stakeholder - Person & Title | Internal Stakeholder - Person & Title | Activity | % complete | Start | Finish | Duration | Effort | Effort completed | Effort remaining | Dependents (after) | Depends on | Labels | Grants Systems Projects | Milestone | Notes | Completed | Checklist Items | Goal | Work Type | Primary Number | Secondary Number | Primary and Secondary Index | Third Number | Is Primary Header | Primary Name | Has Second Header | Secondary Name | Has Third Header | Third Name | Duration Resolved
1 | 1.1.1 | Urgent | Backlog | Dummy task 001 - update Data Integration process | Dummy completion criteria for task 001; outcome reviewed and recorded. | Approval / Sign Off | Taylor Brooks | 2026-09-22 | Resolved | The Department of Health and Aged Care (DoHAC) | DUMMY-397261 | Senior Advisor, Grants Policy | Project Officer | Issue / bug | 100 | 2026-08-17 | 2026-09-22 | 36 days | 16 | 16 | 0 |  |  | Data Management;Reporting;Governance and Change Control;Data Model | Workflow Modernisation | Milestone 3 | Dummy notes for synthetic test row 001. | 2026-09-22 | Draft; Review; Close | Dummy goal improve tracking | Transformation | 1 | 1 | 1.1 | 1 | FALSE | GSI - Systems Support | TRUE | Stakeholder Engagement | TRUE | Implementation | Less than 1 Month
2 | 1.1.2 | Medium | Sep25 Oct25 | Dummy task 002 - validate GPM process | Dummy completion criteria for task 002; outcome reviewed and recorded. | Design / Co-design | Morgan Blake | 2026-09-22 | For Triage | GB Grants Projects | DUMMY-839289 | Director, Program Office | System Owner | Change | 100 | 2026-08-18 | 2026-09-22 | 35 days | 24 | 24 | 0 |  |  | Business Improvement;Governance and Change Control;Communication and Collaboration | GEM | Milestone 2 | Dummy notes for synthetic test row 002. | 2026-09-22 | Prepare; Validate; Approve | Dummy goal validate data quality | Corporate Contributions | 1 | 1 | 1.1 | 2 | FALSE | GSI - Governance and Assurance | TRUE | Data Remediation | FALSE |  | 1 Month
3 | 1.1.3 | High | Dec25 Jan26 | Dummy task 003 - configure Workflow Modernisation process | Dummy completion criteria for task 003; outcome reviewed and recorded. | Build / Drafting | Alex Taylor |  | Backlog | Other | DUMMY-386819 | Director, Program Office | Product Lead | Change | 75 | 2026-08-04 | 2026-08-16 | 12 days | 32 | 24 | 8 | 4 |  | Governance and Change Control;GEM;Systems Admin;Grants Tool Kit | Workflow Modernisation | Milestone 1 | Dummy notes for synthetic test row 003. |  | Prepare; Validate; Approve | Dummy goal reduce manual effort | Transformation | 1 | 1 | 1.1 | 3 | FALSE | GSI - Governance and Assurance | TRUE | Dashboard Maintenance | TRUE | Review | Greater than 1 Month
4 | 1.1.4 | Urgent | Sep26 Oct26 | Dummy task 004 - document Grant Reporting Hub process | Dummy completion criteria for task 004; outcome reviewed and recorded. | Test / Review | Morgan Blake |  | Doing | Procurement Advisory Section | DUMMY-758445 | Senior Advisor, Grants Policy | Product Lead | Maintain | 0 | 2026-07-18 | 2026-08-07 | 20 days | 32 | 0 | 32 |  | 3 | Data Management;EGEM;Reporting;Analysis & Advice;Systems Admin | Data Integration | Milestone 2 | Dummy notes for synthetic test row 004. |  | Draft; Review; Close | Dummy goal reduce manual effort | Corporate Contributions | 1 | 1 | 1.1 | 4 | FALSE | GSI - Reporting Improvements | TRUE | Process Improvement | TRUE | Closure | 1 Month
5 | 1.1.5 | High | Feb26 | Dummy task 005 - review Workflow Modernisation process | Dummy completion criteria for task 005; outcome reviewed and recorded. | Approval / Sign Off | Taylor Brooks |  | To Do | Grants Branch Managers Office | DUMMY-447965 | Business Owner, Reporting | System Owner | New | 0 | 2026-07-08 | 2026-07-14 | 6 days | 24 | 0 | 24 |  |  | GEM;Analysis & Advice | Data Integration |  | Dummy notes for synthetic test row 005. |  | Prepare; Validate; Approve | Dummy goal improve tracking | Corporate Contributions | 1 | 1 | 1.1 | 5 | FALSE | GSI - Systems Support | TRUE | Operational Support | TRUE | Implementation | Greater than 1 Month
6 | 1.2.1 | High | Feb26 | Dummy task 006 - review Workflow Modernisation process | Dummy completion criteria for task 006; outcome reviewed and recorded. | Personal | Morgan Blake | 2026-08-23 | Resolved | GB Grant Systems and Innovation | DUMMY-133237 | Director, Program Office | Business Analyst | Change | 100 | 2026-07-10 | 2026-08-23 | 44 days | 8 | 8 | 0 |  |  | GPS;Data Management;Reporting | GEM |  | Dummy notes for synthetic test row 006. | 2026-08-23 |  | Dummy goal validate data quality | Program Management | 1 | 2 | 1.2 | 1 | FALSE | GSI - Systems Support | TRUE | Dashboard Maintenance | TRUE | Build | 1 Month
7 | 1.2.2 | Medium | Nov25 | Dummy task 007 - configure Data Integration process | Dummy completion criteria for task 007; outcome reviewed and recorded. | Test / Review | Riley Chen |  | Backlog | Ministers Office | DUMMY-668834 | Director, Program Office | Project Officer | Maintain | 25 | 2026-08-02 | 2026-08-23 | 21 days | 12 | 3 | 9 | 8 |  | Business Improvement;GPM;Reporting;Business As Usual;Grant Connect | Data Integration |  | Dummy notes for synthetic test row 007. |  | Draft; Review; Close | Dummy goal validate data quality | Continuous Improvement | 1 | 2 | 1.2 | 2 | FALSE | GSI - Systems Support | TRUE | Operational Support | FALSE |  | TBA
8 | 1.2.3 | Low | May26 | Dummy task 008 - configure GPM process | Dummy completion criteria for task 008; outcome reviewed and recorded. | Publish / Handover | Riley Chen |  | Backlog | Grants Branch Managers Office | DUMMY-169409 | Business Owner, Reporting | Product Lead | Issue / bug | 75 | 2026-08-23 | 2026-09-03 | 11 days | 4 | 3 | 1 |  | 7 | SAP;GSI Administration;Business As Usual | GEM | Milestone 1 | Dummy notes for synthetic test row 008. |  | Draft; Review; Close | Dummy goal reduce manual effort | Operations | 1 | 2 | 1.2 | 3 | FALSE | GSI - Portfolio Management | TRUE | Data Remediation | FALSE |  | TBA
9 | 1.2.4 | Low | Backlog | Dummy task 009 - update GPM process | Dummy completion criteria for task 009; outcome reviewed and recorded. | Design / Co-design | Jamie Wilson | 2026-10-10 | No Further Action | Grants Branch Managers Office | DUMMY-789196 | Senior Advisor, Grants Policy | Data Analyst | Maintain | 100 | 2026-09-01 | 2026-10-10 | 39 days | 40 | 40 | 0 |  |  | Systems Admin | Grant Reporting Hub |  | Dummy notes for synthetic test row 009. | 2026-10-10 |  | Dummy goal support reporting | Operations | 1 | 2 | 1.2 | 4 | FALSE | GSI - Data Quality | TRUE | Automation Backlog | TRUE | Implementation | Less than 1 Month
10 | 1.2.5 | Low | May26 | Dummy task 010 - configure EGEM process | Dummy completion criteria for task 010; outcome reviewed and recorded. | Publish / Handover | Taylor Brooks |  | For Triage | Program and Policy Areas | DUMMY-499907 | Business Owner, Reporting | Product Lead | Change | 50 | 2026-07-09 | 2026-08-12 | 34 days | 4 | 2 | 2 | 11 |  | GEM;GPM;Governance and Change Control;Business As Usual;Communication and Collaboration | EGEM | Milestone 1 | Dummy notes for synthetic test row 010. |  | Draft; Review; Close | Dummy goal validate data quality | Corporate Contributions | 1 | 2 | 1.2 | 5 | FALSE | GSI - Reporting Improvements | TRUE | Stakeholder Engagement | FALSE |  | Greater than 1 Month
11 | 2.3.1 | Urgent | Nov26 | Dummy task 011 - update Workflow Modernisation process | Dummy completion criteria for task 011; outcome reviewed and recorded. | Test / Review | Jamie Wilson |  | No Further Action | Procurement Advisory Section | DUMMY-401079 | Manager, Finance Liaison | Product Lead | Change | 25 | 2026-08-23 | 2026-09-09 | 17 days | 8 | 2 | 6 |  | 10 | GPM;Data Management;Business Improvement;Communication and Collaboration;Systems Admin | Grant Reporting Hub |  | Dummy notes for synthetic test row 011. |  |  | Dummy goal support reporting | Operations | 2 | 3 | 2.3 | 1 | FALSE | GSI - Systems Support | TRUE | Data Remediation | FALSE |  | 1 Month
12 | 2.3.2 | Urgent | Nov26 | Dummy task 012 - configure EGEM process | Dummy completion criteria for task 012; outcome reviewed and recorded. | Design / Co-design | Sam Patel | 2026-08-12 | No Further Action | Other | DUMMY-876449 | Senior Advisor, Grants Policy | Business Analyst | New | 100 | 2026-07-18 | 2026-08-12 | 25 days | 24 | 24 | 0 |  |  | Business As Usual;Governance and Change Control;Communication and Collaboration | Data Integration |  | Dummy notes for synthetic test row 012. | 2026-08-12 | Draft; Review; Close | Dummy goal improve tracking | Program Management | 2 | 3 | 2.3 | 2 | FALSE | GSI - Portfolio Management | TRUE | Automation Backlog | TRUE | Implementation | Greater than 1 Month
13 | 2.3.3 | Urgent | Dec25 Jan26 | Dummy task 013 - update Workflow Modernisation process | Dummy completion criteria for task 013; outcome reviewed and recorded. | Personal | Jamie Wilson |  | Doing | GB Strategy and Coordination | DUMMY-118406 | Senior Advisor, Grants Policy | Data Analyst | Maintain | 50 | 2026-07-24 | 2026-08-29 | 36 days | 12 | 6 | 6 |  |  | Reporting;Analysis & Advice;Data Model | GPM |  | Dummy notes for synthetic test row 013. |  | Prepare; Validate; Approve | Dummy goal support reporting | Program Management | 2 | 3 | 2.3 | 3 | FALSE | GSI - Systems Support | TRUE | Automation Backlog | TRUE | Implementation | 1 Month
14 | 2.3.4 | High | Dec26 Jan27 | Dummy task 014 - validate Data Integration process | Dummy completion criteria for task 014; outcome reviewed and recorded. | Discovery / Consult | Jordan Lee |  | Doing | Grants Branch | DUMMY-142404 | Senior Advisor, Grants Policy | System Owner | Maintain | 75 | 2026-07-17 | 2026-07-30 | 13 days | 4 | 3 | 1 | 15 | 13 | Training Material;GSI Administration | Grant Reporting Hub |  | Dummy notes for synthetic test row 014. |  | Draft; Review; Close | Dummy goal validate data quality | Continuous Improvement | 2 | 3 | 2.3 | 4 | FALSE | GSI - Reporting Improvements | TRUE | Planning and Intake | TRUE | Discovery | TBA
15 | 2.3.5 | High | Backlog | Dummy task 015 - validate Grant Reporting Hub process | Dummy completion criteria for task 015; outcome reviewed and recorded. | Design / Co-design | Jamie Wilson |  | To Do | GB Policy Governance and Assurance | DUMMY-449879 | Senior Advisor, Grants Policy | System Owner | Issue / bug | 0 | 2026-08-09 | 2026-08-14 | 5 days | 4 | 0 | 4 |  |  | GEM;GPM;Reporting;Systems Admin | Data Integration |  | Dummy notes for synthetic test row 015. |  | Draft; Review; Close | Dummy goal support reporting | Corporate Contributions | 2 | 3 | 2.3 | 5 | FALSE | GSI - Systems Support | TRUE | Planning and Intake | FALSE |  | TBA
16 | 2.4.1 | Low | Backlog | Dummy task 016 - configure GPM process | Dummy completion criteria for task 016; outcome reviewed and recorded. | Personal | Casey Morgan |  | No Further Action | GB Assessment Centre | DUMMY-844841 | Manager, Finance Liaison | Business Analyst | New | 75 | 2026-08-03 | 2026-08-11 | 8 days | 12 | 9 | 3 |  |  | Data Management;Business As Usual;Reporting;Analysis & Advice | GPM |  | Dummy notes for synthetic test row 016. |  | Prepare; Validate; Approve | Dummy goal improve tracking | Transformation | 2 | 4 | 2.4 | 1 | FALSE | GSI - Portfolio Management | TRUE | Planning and Intake | FALSE |  | 1 Month
17 | 2.4.2 | Urgent | Feb26 | Dummy task 017 - document EGEM process | Dummy completion criteria for task 017; outcome reviewed and recorded. | Approval / Sign Off | Riley Chen |  | To Do | Procurement Advisory Section | DUMMY-424747 | Business Owner, Reporting | Project Officer | Change | 0 | 2026-09-25 | 2026-10-29 | 34 days | 16 | 0 | 16 | 18 |  | Business As Usual;GSI Administration;Governance and Change Control | GPM |  | Dummy notes for synthetic test row 017. |  | Prepare; Validate; Approve | Dummy goal validate data quality | Corporate Contributions | 2 | 4 | 2.4 | 2 | FALSE | GSI - Governance and Assurance | TRUE | Automation Backlog | TRUE | Build | Less than 1 Month
18 | 2.4.3 | Medium | Dec25 Jan26 | Dummy task 018 - document Data Integration process | Dummy completion criteria for task 018; outcome reviewed and recorded. | Test / Review | Alex Taylor |  | Doing | GB Hub Operations | DUMMY-503697 | Business Owner, Reporting | Business Analyst | New | 50 | 2026-07-21 | 2026-08-09 | 19 days | 40 | 20 | 20 |  |  | GSI Administration;Communication and Collaboration;Project Planning | Workflow Modernisation |  | Dummy notes for synthetic test row 018. |  | Draft; Review; Close | Dummy goal support reporting | Operations | 2 | 4 | 2.4 | 3 | FALSE | GSI - Systems Support | TRUE | Process Improvement | TRUE | Discovery | 1 Month
19 | 2.4.4 | Low | Dec25 Jan26 | Dummy task 019 - review Data Integration process | Dummy completion criteria for task 019; outcome reviewed and recorded. | Test / Review | Jamie Wilson |  | To Do | GB Infrastructure and Policy | DUMMY-484715 | Director, Program Office | System Owner | Change | 0 | 2026-08-23 | 2026-09-24 | 32 days | 8 | 0 | 8 | 20 | 18 | EGEM;Communication and Collaboration | GEM |  | Dummy notes for synthetic test row 019. |  |  | Dummy goal reduce manual effort | Operations | 2 | 4 | 2.4 | 4 | FALSE | GSI - Systems Support | TRUE | Operational Support | TRUE | Review | Less than 1 Month
20 | 2.4.5 | Medium | Dec25 Jan26 | Dummy task 020 - test Workflow Modernisation process | Dummy completion criteria for task 020; outcome reviewed and recorded. | Design / Co-design | Jamie Wilson |  | To Do | Ministers Office | DUMMY-640377 | Senior Advisor, Grants Policy | Project Officer | Change | 0 | 2026-08-21 | 2026-09-05 | 15 days | 40 | 0 | 40 | 21 | 19 | Training & Communications ;Data Management | EGEM | Milestone 2 | Dummy notes for synthetic test row 020. |  | Draft; Review; Close | Dummy goal validate data quality | Operations | 2 | 4 | 2.4 | 5 | FALSE | GSI - Data Quality | TRUE | Process Improvement | FALSE |  | TBA
21 | 3.5.1 | High | Dec25 Jan26 | Dummy task 021 - configure EGEM process | Dummy completion criteria for task 021; outcome reviewed and recorded. | Build / Drafting | Taylor Brooks |  | No Further Action | GB Strategy and Coordination | DUMMY-776146 | Director, Program Office | Data Analyst | Issue / bug | 75 | 2026-08-14 | 2026-08-27 | 13 days | 32 | 24 | 8 |  | 20 | Business As Usual;GSI Administration;Communication and Collaboration;Professional Development | EGEM |  | Dummy notes for synthetic test row 021. |  | Prepare; Validate; Approve | Dummy goal validate data quality | Transformation | 3 | 5 | 3.5 | 1 | FALSE | GSI - Systems Support | TRUE | Process Improvement | TRUE | Implementation | Greater than 1 Month
22 | 3.5.2 | Low | Dec25 Jan26 | Dummy task 022 - document Grant Reporting Hub process | Dummy completion criteria for task 022; outcome reviewed and recorded. | Test / Review | Sam Patel |  | No Further Action | GB Assessment Centre | DUMMY-534839 | Director, Program Office | Business Analyst | Change | 0 | 2026-08-25 | 2026-10-07 | 43 days | 4 | 0 | 4 |  |  | GPM;GEM | Grant Reporting Hub |  | Dummy notes for synthetic test row 022. |  | Prepare; Validate; Approve | Dummy goal validate data quality | Transformation | 3 | 5 | 3.5 | 2 | FALSE | GSI - Governance and Assurance | TRUE | Planning and Intake | FALSE |  | Less than 1 Month
23 | 3.5.3 | Low | Nov25 | Dummy task 023 - review EGEM process | Dummy completion criteria for task 023; outcome reviewed and recorded. | Test / Review | Jamie Wilson |  | Backlog | GB Strategy and Coordination | DUMMY-325228 | Business Owner, Reporting | Product Lead | Maintain | 50 | 2026-09-14 | 2026-10-16 | 32 days | 40 | 20 | 20 | 24 | 22 | Business Improvement;Reporting;Systems Admin;Grant Connect;Data Management | Grant Reporting Hub |  | Dummy notes for synthetic test row 023. |  |  | Dummy goal improve tracking | Operations | 3 | 5 | 3.5 | 3 | FALSE | GSI - Reporting Improvements | TRUE | Dashboard Maintenance | TRUE | Build | Less than 1 Month
24 | 3.5.4 | High | Feb26 | Dummy task 024 - update GPM process | Dummy completion criteria for task 024; outcome reviewed and recorded. | Personal | Casey Morgan |  | To Do | GB Policy Governance and Assurance | DUMMY-508731 | Business Owner, Reporting | System Owner | Maintain | 0 | 2026-09-20 | 2026-10-26 | 36 days | 12 | 0 | 12 |  |  | Governance and Change Control;Systems Admin | Data Integration | Milestone 3 | Dummy notes for synthetic test row 024. |  |  | Dummy goal support reporting | Corporate Contributions | 3 | 5 | 3.5 | 4 | FALSE | GSI - Reporting Improvements | TRUE | Automation Backlog | TRUE | Build | Greater than 1 Month
25 | 3.5.5 | Low | Dec25 Jan26 | Dummy task 025 - document GPM process | Dummy completion criteria for task 025; outcome reviewed and recorded. | Approval / Sign Off | Taylor Brooks |  | For Triage | GB Grants Projects | DUMMY-447434 | Senior Advisor, Grants Policy | System Owner | New | 0 | 2026-09-26 | 2026-10-29 | 33 days | 12 | 0 | 12 |  | 24 | Business Improvement;Reporting;Systems Admin;Grant Connect;Data Management | GPM |  | Dummy notes for synthetic test row 025. |  |  | Dummy goal validate data quality | Corporate Contributions | 3 | 5 | 3.5 | 5 | FALSE | GSI - Portfolio Management | TRUE | Dashboard Maintenance | FALSE |  | 1 Month
26 | 3.6.1 | Medium | Sep25 Oct25 | Dummy task 026 - validate EGEM process | Dummy completion criteria for task 026; outcome reviewed and recorded. | Publish / Handover | Jamie Wilson |  | No Further Action | Procurement Advisory Section | DUMMY-247266 | Director, Program Office | Business Analyst | Maintain | 0 | 2026-07-10 | 2026-07-16 | 6 days | 40 | 0 | 40 |  |  | EGEM;Reporting | GPM | Milestone 2 | Dummy notes for synthetic test row 026. |  |  | Dummy goal support reporting | Continuous Improvement | 3 | 6 | 3.6 | 1 | FALSE | GSI - Reporting Improvements | TRUE | Process Improvement | FALSE |  | Greater than 1 Month
27 | 3.6.2 | Low | Feb26 | Dummy task 027 - update GPM process | Dummy completion criteria for task 027; outcome reviewed and recorded. | Discovery / Consult | Casey Morgan |  | Doing | GB Grant Design | DUMMY-996565 | Director, Program Office | Product Lead | Maintain | 0 | 2026-07-13 | 2026-07-16 | 3 days | 8 | 0 | 8 |  |  | GPM;Business Improvement;Governance and Change Control | Workflow Modernisation | Milestone 1 | Dummy notes for synthetic test row 027. |  | Prepare; Validate; Approve | Dummy goal support reporting | Corporate Contributions | 3 | 6 | 3.6 | 2 | FALSE | GSI - Systems Support | TRUE | Data Remediation | FALSE |  | Greater than 1 Month
28 | 3.6.3 | Urgent | Dec25 Jan26 | Dummy task 028 - validate GEM process | Dummy completion criteria for task 028; outcome reviewed and recorded. | Approval / Sign Off | Jamie Wilson |  | Doing | Grants Branch Managers Office | DUMMY-334761 | Senior Advisor, Grants Policy | System Owner | Change | 0 | 2026-09-22 | 2026-10-13 | 21 days | 4 | 0 | 4 |  |  | Data Management | Grant Reporting Hub |  | Dummy notes for synthetic test row 028. |  |  | Dummy goal improve tracking | Program Management | 3 | 6 | 3.6 | 3 | FALSE | GSI - Portfolio Management | TRUE | Planning and Intake | TRUE | Review | 1 Month
29 | 3.6.4 | Low | Jun26 Jul26 | Dummy task 029 - test EGEM process | Dummy completion criteria for task 029; outcome reviewed and recorded. | Publish / Handover | Riley Chen | 2026-07-13 | Resolved | The Department of Health and Aged Care (DoHAC) | DUMMY-434480 | Manager, Finance Liaison | Project Officer | Change | 100 | 2026-07-02 | 2026-07-13 | 11 days | 32 | 32 | 0 | 30 | 28 | Data Management;Systems Admin;GSI Administration | GPM | Milestone 1 | Dummy notes for synthetic test row 029. | 2026-07-13 | Draft; Review; Close | Dummy goal support reporting | Corporate Contributions | 3 | 6 | 3.6 | 4 | FALSE | GSI - Governance and Assurance | TRUE | Dashboard Maintenance | TRUE | Review | Greater than 1 Month
30 | 3.6.5 | High | Feb26 | Dummy task 030 - update Data Integration process | Dummy completion criteria for task 030; outcome reviewed and recorded. | Approval / Sign Off | Jamie Wilson |  | For Triage | GB Policy Governance and Assurance | DUMMY-188407 | Business Owner, Reporting | Business Analyst | Maintain | 75 | 2026-08-08 | 2026-09-07 | 30 days | 32 | 24 | 8 |  | 29 | GPM | GEM |  | Dummy notes for synthetic test row 030. |  | Prepare; Validate; Approve | Dummy goal improve tracking | Continuous Improvement | 3 | 6 | 3.6 | 5 | FALSE | GSI - Portfolio Management | TRUE | Operational Support | TRUE | Review | 1 Month
31 | 4.7.1 | Urgent | Backlog | Dummy task 031 - review GPM process | Dummy completion criteria for task 031; outcome reviewed and recorded. | Publish / Handover | Sam Patel |  | Doing | Program and Policy Areas | DUMMY-231146 | Manager, Finance Liaison | Business Analyst | New | 50 | 2026-08-26 | 2026-09-11 | 16 days | 4 | 2 | 2 | 32 |  | Data Management;Analysis & Advice;Business Improvement | GPM | Milestone 4 | Dummy notes for synthetic test row 031. |  | Draft; Review; Close | Dummy goal improve tracking | Program Management | 4 | 7 | 4.7 | 1 | FALSE | GSI - Data Quality | TRUE | Data Remediation | FALSE |  | 1 Month
32 | 4.7.2 | Urgent | Jun26 Jul26 | Dummy task 032 - update Grant Reporting Hub process | Dummy completion criteria for task 032; outcome reviewed and recorded. | Personal | Morgan Blake |  | For Triage | Grants Branch Managers Office | DUMMY-777231 | Senior Advisor, Grants Policy | Business Analyst | Change | 0 | 2026-08-26 | 2026-09-21 | 26 days | 32 | 0 | 32 |  |  | Business As Usual;GSI Administration;Communication and Collaboration | Grant Reporting Hub |  | Dummy notes for synthetic test row 032. |  |  | Dummy goal support reporting | Corporate Contributions | 4 | 7 | 4.7 | 2 | FALSE | GSI - Systems Support | TRUE | Planning and Intake | TRUE | Review | Less than 1 Month
33 | 4.7.3 | Low | Mar 26 Apr26 | Dummy task 033 - configure Data Integration process | Dummy completion criteria for task 033; outcome reviewed and recorded. | Design / Co-design | Casey Morgan |  | Backlog | GB Hub Operations | DUMMY-770686 | Senior Advisor, Grants Policy | System Owner | New | 75 | 2026-07-16 | 2026-07-28 | 12 days | 12 | 9 | 3 |  | 32 | Training & Communications ;Reporting;Data Management;Business Improvement | Data Integration | Milestone 4 | Dummy notes for synthetic test row 033. |  |  | Dummy goal reduce manual effort | Corporate Contributions | 4 | 7 | 4.7 | 3 | FALSE | GSI - Systems Support | TRUE | Data Remediation | TRUE | Implementation | 1 Month
34 | 4.7.4 | High | May26 | Dummy task 034 - document Workflow Modernisation process | Dummy completion criteria for task 034; outcome reviewed and recorded. | Design / Co-design | Alex Taylor |  | For Triage | Grants Branch Managers Office | DUMMY-754278 | Director, Program Office | Business Analyst | Maintain | 75 | 2026-07-30 | 2026-08-26 | 27 days | 24 | 18 | 6 |  | 33 | Analysis & Advice;Governance and Change Control;Communication and Collaboration | Workflow Modernisation |  | Dummy notes for synthetic test row 034. |  | Prepare; Validate; Approve | Dummy goal reduce manual effort | Program Management | 4 | 7 | 4.7 | 4 | FALSE | GSI - Data Quality | TRUE | Operational Support | TRUE | Review | TBA
35 | 4.7.5 | Urgent | Aug26 | Dummy task 035 - test EGEM process | Dummy completion criteria for task 035; outcome reviewed and recorded. | Test / Review | Casey Morgan | 2026-09-28 | Backlog | Other | DUMMY-197868 | Manager, Finance Liaison | Project Officer | Change | 100 | 2026-08-19 | 2026-09-28 | 40 days | 24 | 24 | 0 |  | 34 | GPM;Business Improvement;Communication and Collaboration;Systems Admin;Data Management | GEM | Milestone 3 | Dummy notes for synthetic test row 035. | 2026-09-28 | Draft; Review; Close | Dummy goal support reporting | Continuous Improvement | 4 | 7 | 4.7 | 5 | FALSE | GSI - Governance and Assurance | TRUE | Dashboard Maintenance | TRUE | Build | 1 Month
36 | 4.1.1 | Low | Sep26 Oct26 | Dummy task 036 - document GEM process | Dummy completion criteria for task 036; outcome reviewed and recorded. | Publish / Handover | Jamie Wilson | 2026-09-02 | Doing | Other | DUMMY-193683 | Manager, Finance Liaison | Data Analyst | Change | 100 | 2026-08-03 | 2026-09-02 | 30 days | 12 | 12 | 0 |  |  | GPS;Reporting;Systems Admin;Data Management | Data Integration |  | Dummy notes for synthetic test row 036. | 2026-09-02 |  | Dummy goal support reporting | Corporate Contributions | 4 | 1 | 4.1 | 1 | FALSE | GSI - Data Quality | TRUE | Data Remediation | FALSE |  | TBA
37 | 4.1.2 | Medium | Sep26 Oct26 | Dummy task 037 - test Data Integration process | Dummy completion criteria for task 037; outcome reviewed and recorded. | Discovery / Consult | Sam Patel |  | For Triage | Procurement Advisory Section | DUMMY-613597 | Director, Program Office | Project Officer | Maintain | 50 | 2026-08-05 | 2026-09-10 | 36 days | 32 | 16 | 16 | 38 |  | Business Improvement;Governance and Change Control;Data Management;Reporting;Communication and Collaboration | EGEM |  | Dummy notes for synthetic test row 037. |  | Prepare; Validate; Approve | Dummy goal reduce manual effort | Transformation | 4 | 1 | 4.1 | 2 | FALSE | GSI - Reporting Improvements | TRUE | Data Remediation | TRUE | Discovery | 1 Month
38 | 4.1.3 | High | Feb26 | Dummy task 038 - review EGEM process | Dummy completion criteria for task 038; outcome reviewed and recorded. | Approval / Sign Off | Morgan Blake |  | Backlog | Program and Policy Areas | DUMMY-987750 | Manager, Finance Liaison | Business Analyst | Maintain | 0 | 2026-09-05 | 2026-09-17 | 12 days | 12 | 0 | 12 | 39 |  | Data Management;GEM;GPM;Governance and Change Control;Professional Development;GSI Administration;Training Material;Business Improvement;Training & Communications ;Communication and Collaboration | GEM | Milestone 3 | Dummy notes for synthetic test row 038. |  |  | Dummy goal validate data quality | Continuous Improvement | 4 | 1 | 4.1 | 3 | FALSE | GSI - Governance and Assurance | TRUE | Stakeholder Engagement | TRUE | Discovery | TBA
39 | 4.1.4 | Urgent | Feb26 | Dummy task 039 - document Grant Reporting Hub process | Dummy completion criteria for task 039; outcome reviewed and recorded. | Approval / Sign Off | Jordan Lee |  | For Triage | Grants Branch Managers Office | DUMMY-385216 | Business Owner, Reporting | Product Lead | Change | 50 | 2026-08-26 | 2026-10-03 | 38 days | 4 | 2 | 2 | 40 |  | Reporting;Altus;Governance and Change Control;Business As Usual | GPM | Milestone 4 | Dummy notes for synthetic test row 039. |  |  | Dummy goal support reporting | Operations | 4 | 1 | 4.1 | 4 | FALSE | GSI - Reporting Improvements | TRUE | Data Remediation | TRUE | Implementation | TBA
40 | 4.1.5 | Low | Feb26 | Dummy task 040 - document GPM process | Dummy completion criteria for task 040; outcome reviewed and recorded. | Publish / Handover | Riley Chen |  | To Do | GB Hub Operations | DUMMY-589899 | Manager, Finance Liaison | Business Analyst | Issue / bug | 0 | 2026-09-21 | 2026-10-18 | 27 days | 8 | 0 | 8 | 41 | 39 | Data Management;Reporting;Governance and Change Control;Communication and Collaboration | Grant Reporting Hub | Milestone 3 | Dummy notes for synthetic test row 040. |  | Draft; Review; Close | Dummy goal support reporting | Corporate Contributions | 4 | 1 | 4.1 | 5 | FALSE | GSI - Reporting Improvements | TRUE | Automation Backlog | FALSE |  | Less than 1 Month
41 | 5.2.1 | High | Mar 26 Apr26 | Dummy task 041 - test EGEM process | Dummy completion criteria for task 041; outcome reviewed and recorded. | Build / Drafting | Sam Patel |  | For Triage | GB Infrastructure and Policy | DUMMY-208941 | Business Owner, Reporting | Business Analyst | New | 50 | 2026-07-03 | 2026-07-13 | 10 days | 4 | 2 | 2 |  |  | Reporting;GSI Administration;Business Improvement | Workflow Modernisation |  | Dummy notes for synthetic test row 041. |  | Prepare; Validate; Approve | Dummy goal improve tracking | Corporate Contributions | 5 | 2 | 5.2 | 1 | FALSE | GSI - Portfolio Management | TRUE | Operational Support | FALSE |  | Greater than 1 Month
42 | 5.2.2 | Urgent | Nov26 | Dummy task 042 - test GEM process | Dummy completion criteria for task 042; outcome reviewed and recorded. | Personal | Taylor Brooks | 2026-09-07 | For Triage | Other | DUMMY-591094 | Director, Program Office | Project Officer | Issue / bug | 100 | 2026-08-25 | 2026-09-07 | 13 days | 4 | 4 | 0 |  |  | Business Improvement;Project Planning | GEM | Milestone 1 | Dummy notes for synthetic test row 042. | 2026-09-07 | Prepare; Validate; Approve | Dummy goal reduce manual effort | Continuous Improvement | 5 | 2 | 5.2 | 2 | FALSE | GSI - Data Quality | TRUE | Planning and Intake | FALSE |  | TBA
43 | 5.2.3 | Medium | Aug26 | Dummy task 043 - document GPM process | Dummy completion criteria for task 043; outcome reviewed and recorded. | Approval / Sign Off | Alex Taylor | 2026-08-22 | Resolved | The Department of Health and Aged Care (DoHAC) | DUMMY-631426 | Director, Program Office | Project Officer | Change | 100 | 2026-07-29 | 2026-08-22 | 24 days | 4 | 4 | 0 |  |  | GEM;Training & Communications | Grant Reporting Hub |  | Dummy notes for synthetic test row 043. | 2026-08-22 |  | Dummy goal reduce manual effort | Operations | 5 | 2 | 5.2 | 3 | FALSE | GSI - Reporting Improvements | TRUE | Data Remediation | FALSE |  | Greater than 1 Month
44 | 5.2.4 | High | Feb26 | Dummy task 044 - review GPM process | Dummy completion criteria for task 044; outcome reviewed and recorded. | Design / Co-design | Casey Morgan |  | To Do | Grants Branch | DUMMY-266556 | Manager, Finance Liaison | Project Officer | Change | 0 | 2026-07-31 | 2026-08-21 | 21 days | 12 | 0 | 12 |  |  | EGEM;Training Material | Workflow Modernisation |  | Dummy notes for synthetic test row 044. |  | Draft; Review; Close | Dummy goal reduce manual effort | Transformation | 5 | 2 | 5.2 | 4 | FALSE | GSI - Reporting Improvements | TRUE | Automation Backlog | TRUE | Review | 1 Month
45 | 5.2.5 | Urgent | Nov25 | Dummy task 045 - update GEM process | Dummy completion criteria for task 045; outcome reviewed and recorded. | Publish / Handover | Jamie Wilson | 2026-10-05 | Doing | Grants Branch | DUMMY-385509 | Senior Advisor, Grants Policy | Product Lead | New | 100 | 2026-09-18 | 2026-10-05 | 17 days | 12 | 12 | 0 | 46 | 44 | GPM;GEM;EGEM;GPS;Reporting;Training Material;Systems Admin | Data Integration |  | Dummy notes for synthetic test row 045. | 2026-10-05 | Draft; Review; Close | Dummy goal improve tracking | Program Management | 5 | 2 | 5.2 | 5 | FALSE | GSI - Reporting Improvements | TRUE | Planning and Intake | TRUE | Build | Greater than 1 Month
46 | 5.3.1 | High | Sep26 Oct26 | Dummy task 046 - review Data Integration process | Dummy completion criteria for task 046; outcome reviewed and recorded. | Design / Co-design | Morgan Blake |  | Doing | GB Policy Governance and Assurance | DUMMY-386916 | Manager, Finance Liaison | Data Analyst | Issue / bug | 75 | 2026-09-14 | 2026-10-10 | 26 days | 4 | 3 | 1 |  | 45 | Business Improvement;Governance and Change Control;Communication and Collaboration;Data Management;GSI Administration | GPM |  | Dummy notes for synthetic test row 046. |  | Draft; Review; Close | Dummy goal reduce manual effort | Transformation | 5 | 3 | 5.3 | 1 | FALSE | GSI - Portfolio Management | TRUE | Stakeholder Engagement | TRUE | Closure | 1 Month
47 | 5.3.2 | Medium | Nov26 | Dummy task 047 - validate Data Integration process | Dummy completion criteria for task 047; outcome reviewed and recorded. | Build / Drafting | Riley Chen | 2026-10-04 | Resolved | GB Hub Operations | DUMMY-324929 | Director, Program Office | Data Analyst | Change | 100 | 2026-08-23 | 2026-10-04 | 42 days | 24 | 24 | 0 |  |  | EGEM;Data Management;GSI Administration;Communication and Collaboration;Governance and Change Control | Workflow Modernisation |  | Dummy notes for synthetic test row 047. | 2026-10-04 |  | Dummy goal support reporting | Program Management | 5 | 3 | 5.3 | 2 | FALSE | GSI - Governance and Assurance | TRUE | Automation Backlog | FALSE |  | Less than 1 Month
48 | 5.3.3 | Urgent | Mar 26 Apr26 | Dummy task 048 - document EGEM process | Dummy completion criteria for task 048; outcome reviewed and recorded. | Approval / Sign Off | Riley Chen | 2026-08-17 | For Triage | Grants Branch Managers Office | DUMMY-464489 | Business Owner, Reporting | Product Lead | Issue / bug | 100 | 2026-08-05 | 2026-08-17 | 12 days | 40 | 40 | 0 |  |  | Governance and Change Control;Business As Usual;Communication and Collaboration | Data Integration | Milestone 2 | Dummy notes for synthetic test row 048. | 2026-08-17 | Prepare; Validate; Approve | Dummy goal reduce manual effort | Operations | 5 | 3 | 5.3 | 3 | FALSE | GSI - Reporting Improvements | TRUE | Stakeholder Engagement | TRUE | Discovery | Greater than 1 Month
49 | 5.3.4 | Medium | Jun26 Jul26 | Dummy task 049 - configure Data Integration process | Dummy completion criteria for task 049; outcome reviewed and recorded. | Approval / Sign Off | Casey Morgan |  | For Triage | GB Assessment Centre | DUMMY-508958 | Director, Program Office | System Owner | Change | 25 | 2026-09-01 | 2026-10-15 | 44 days | 8 | 2 | 6 | 50 | 48 | GPM;Training Material;Training & Communications ;Communication and Collaboration;Professional Development;Business As Usual | GEM |  | Dummy notes for synthetic test row 049. |  | Prepare; Validate; Approve | Dummy goal reduce manual effort | Corporate Contributions | 5 | 3 | 5.3 | 4 | FALSE | GSI - Reporting Improvements | TRUE | Stakeholder Engagement | TRUE | Closure | Less than 1 Month
50 | 5.3.5 | High | Jun26 Jul26 | Dummy task 050 - review Workflow Modernisation process | Dummy completion criteria for task 050; outcome reviewed and recorded. | Publish / Handover | Casey Morgan |  | For Triage | Grants Branch Managers Office | DUMMY-534523 | Director, Program Office | Project Officer | Change | 25 | 2026-09-08 | 2026-10-08 | 30 days | 8 | 2 | 6 |  |  | Analysis & Advice;Communication and Collaboration;Business As Usual;Grants Tool Kit | GEM | Milestone 4 | Dummy notes for synthetic test row 050. |  | Draft; Review; Close | Dummy goal reduce manual effort | Continuous Improvement | 5 | 3 | 5.3 | 5 | FALSE | GSI - Governance and Assurance | TRUE | Stakeholder Engagement | FALSE |  | Less than 1 Month

## Original Choice Values Used
Sprint | Bucket | Status | Activity | Labels | Work Type | Stakeholder - Org Unit
Aug26 | Approval / Sign Off | Backlog | Change | Altus | Continuous Improvement | GB Assessment Centre
Backlog | Build / Drafting | Doing | Issue / bug | Altus;Project Planning | Corporate Contributions | GB Grant Design
Dec25 Jan26 | Design / Co-design | For Triage | Maintain | Altus;Reporting;GSI Administration | Operations | GB Grant Systems and Innovation
Dec26 Jan27 | Discovery / Consult | No Further Action | New | Analysis & Advice | Program Management | GB Grants Projects
Feb26 | Personal | Resolved |  | Analysis & Advice;Business As Usual | Transformation | GB Hub Operations
Jun26 Jul26 | Publish / Handover | To Do |  | Analysis & Advice;Business As Usual;Systems Admin |  | GB Infrastructure and Policy
Mar 26 Apr26 | Test / Review |  |  | Analysis & Advice;Business Improvement |  | GB Policy Governance and Assurance
May26 |  |  |  | Analysis & Advice;Business Improvement;Communication and Collaboration |  | GB Strategy and Coordination
Nov25 |  |  |  | Analysis & Advice;Business Improvement;Governance and Change Control |  | Grants Branch
Nov26 |  |  |  | Analysis & Advice;Business Improvement;Governance and Change Control;Professional Development |  | Grants Branch Managers Office
Sep25 Oct25 |  |  |  | Analysis & Advice;Business Improvement;Governance and Change Control;Project Planning;Communication and Collaboration |  | Ministers Office
Sep26 Oct26 |  |  |  | Analysis & Advice;Communication and Collaboration |  | Other
|  |  |  | Analysis & Advice;Communication and Collaboration;Business As Usual;Grants Tool Kit |  | Procurement Advisory Section
|  |  |  | Analysis & Advice;Communication and Collaboration;GSI Administration |  | Program and Policy Areas
|  |  |  | Analysis & Advice;Communication and Collaboration;Governance and Change Control |  | The Department of Health and Aged Care (DoHAC)
Analysis & Advice;Communication and Collaboration;Process Map;Business As Usual
Analysis & Advice;Communication and Collaboration;Professional Development;GSI Administration
Analysis & Advice;GSI Administration;Business As Usual
Analysis & Advice;Governance and Change Control;Business As Usual
Analysis & Advice;Governance and Change Control;Communication and Collaboration
Analysis & Advice;Governance and Change Control;Project Planning;Communication and Collaboration
Analysis & Advice;Project Planning;Business As Usual;GSI Administration;Communication and Collaboration
Analysis & Advice;Reporting;Business Improvement
Business As Usual
Business As Usual;Business Improvement
Business As Usual;Business Improvement;Systems Admin;GSI Administration
Business As Usual;Communication and Collaboration;Project Planning
Business As Usual;Data Management
Business As Usual;Data Management;Governance and Change Control;Reporting
Business As Usual;GEM;Systems Admin
Business As Usual;GSI Administration
Business As Usual;GSI Administration;Communication and Collaboration
Business As Usual;GSI Administration;Communication and Collaboration;Professional Development
Business As Usual;GSI Administration;Governance and Change Control
Business As Usual;Governance and Change Control;Communication and Collaboration
Business As Usual;Professional Development
Business As Usual;Reporting
Business As Usual;Reporting;Analysis & Advice;Project Planning
Business As Usual;Reporting;Communication and Collaboration
Business Improvement
Business Improvement;Analysis & Advice
Business Improvement;Analysis & Advice;Governance and Change Control
Business Improvement;Business As Usual
Business Improvement;Business As Usual;Process Map;Governance and Change Control
Business Improvement;Communication and Collaboration;Governance and Change Control
Business Improvement;Communication and Collaboration;Governance and Change Control;Business As Usual
Business Improvement;GPM;Reporting;Business As Usual;Grant Connect
Business Improvement;Governance and Change Control
Business Improvement;Governance and Change Control;Analysis & Advice
Business Improvement;Governance and Change Control;Communication and Collaboration
Business Improvement;Governance and Change Control;Communication and Collaboration;Data Management;GSI Administration
Business Improvement;Governance and Change Control;Communication and Collaboration;GSI Administration;Professional Development
Business Improvement;Governance and Change Control;Data Management;Reporting;Communication and Collaboration
Business Improvement;Governance and Change Control;GSI Administration
Business Improvement;Governance and Change Control;GSI Administration;Project Planning
Business Improvement;Governance and Change Control;Project Planning
Business Improvement;Governance and Change Control;Reporting;Analysis & Advice;GSI Administration
Business Improvement;Grants Tool Kit;GSI Administration;Governance and Change Control;Systems Admin
Business Improvement;Grants Tool Kit;Process Map
Business Improvement;Process Map;Communication and Collaboration;Systems Admin;Training & Communications ;Project Planning
Business Improvement;Process Map;Governance and Change Control
Business Improvement;Process Map;Systems Admin;GPS;GEM;GPM;Grant Connect;EGEM;Data Management;Governance and Change Control
Business Improvement;Project Planning
Business Improvement;Project Planning;Analysis & Advice;Altus
Business Improvement;Project Planning;Governance and Change Control
Business Improvement;Project Planning;Governance and Change Control;Reporting
Business Improvement;Reporting
Business Improvement;Reporting;Systems Admin;Grant Connect;Data Management
Business Improvement;Systems Admin
Business Improvement;Training & Communications
Business Improvement;Training & Communications ;Project Planning;Governance and Change Control
Business Improvement;Training Material;Process Map;Governance and Change Control
Communication and Collaboration
Communication and Collaboration;Analysis & Advice
Communication and Collaboration;Business As Usual;Governance and Change Control;Project Planning
Communication and Collaboration;Business As Usual;Reporting
Communication and Collaboration;Business Improvement;Systems Admin
Communication and Collaboration;GEM;EGEM;GPM
Communication and Collaboration;GEM;GPM
Communication and Collaboration;GPS;GEM;GPM;EGEM;Reporting;Training Material
Communication and Collaboration;GSI Administration;Business As Usual
Communication and Collaboration;Governance and Change Control
Communication and Collaboration;Grants Tool Kit
Communication and Collaboration;Reporting
Communication and Collaboration;Reporting;Analysis & Advice
Communication and Collaboration;Reporting;Grants Tool Kit
Data Management
Data Management;Analysis & Advice;Business Improvement
Data Management;Business As Usual;Reporting;Analysis & Advice
Data Management;Business Improvement;Governance and Change Control;Data Model
Data Management;Business Improvement;Governance and Change Control;Data Model;Project Planning
Data Management;Business Improvement;Governance and Change Control;Project Planning;Data Model
Data Management;Business Improvement;Process Map
Data Management;Business Improvement;Professional Development;Communication and Collaboration
Data Management;Business Improvement;Project Planning;Governance and Change Control;Data Model
Data Management;Business Improvement;Project Planning;Professional Development;Training & Communications
Data Management;Business Improvement;Training & Communications
Data Management;Communication and Collaboration;Professional Development
Data Management;Data Model;Governance and Change Control;Project Planning;Business Improvement
Data Management;Data Request;Governance and Change Control
Data Management;EGEM;Governance and Change Control;Communication and Collaboration
Data Management;EGEM;Reporting;Analysis & Advice;Systems Admin
Data Management;GEM;GPM;GPS;Reporting;Systems Admin
Data Management;GEM;GPM;Governance and Change Control;Professional Development;GSI Administration;Training Material;Business Improvement;Training & Communications ;Communication and Collaboration
Data Management;GEM;GPS;GPM;EGEM;Grant Connect;Reporting;Business Improvement
Data Management;GEM;Reporting;Business As Usual
Data Management;GEM;Systems Admin
Data Management;GPM;GEM;EGEM;Reporting;Training Material;Business Improvement;Training & Communications ;GSI Administration;Professional Development
Data Management;GPM;Systems Admin
Data Management;GPS;Reporting;Systems Admin;Data Model;GSI Administration
Data Management;GPS;Training Material
Data Management;GSI Administration
Data Management;Grant Connect;GPS;Governance and Change Control
Data Management;Reporting;Altus;SAP;Systems Admin;GSI Administration
Data Management;Reporting;Business As Usual
Data Management;Reporting;Business As Usual;Governance and Change Control
Data Management;Reporting;Business Improvement
Data Management;Reporting;Data Model
Data Management;Reporting;GEM;Systems Admin
Data Management;Reporting;GPS
Data Management;Reporting;GSI Administration
Data Management;Reporting;Governance and Change Control;Communication and Collaboration
Data Management;Reporting;Governance and Change Control;Data Model
Data Management;Reporting;Systems Admin
Data Management;Reporting;Systems Admin;Business As Usual
Data Management;Reporting;Training Material
Data Management;Reporting;Training Material;Governance and Change Control
Data Management;Systems Admin
Data Management;Systems Admin;EGEM
Data Management;Systems Admin;GEM
Data Management;Systems Admin;GSI Administration
Data Management;Systems Admin;Governance and Change Control
Data Model;Reporting;Business Improvement
Data Request
Data Request;Business As Usual
EGEM
EGEM;Communication and Collaboration
EGEM;Data Management;GSI Administration;Communication and Collaboration;Governance and Change Control
EGEM;GPM;GEM
EGEM;GPM;GEM;Grants Tool Kit
EGEM;GPM;GPS;Data Management
EGEM;Grants Tool Kit
EGEM;Reporting
EGEM;Reporting;GSI Administration;Communication and Collaboration
EGEM;Systems Admin
EGEM;Training & Communications
EGEM;Training Material
EGEM;Training Material;Training & Communications ;Communication and Collaboration
GEM
GEM;Analysis & Advice
GEM;Business As Usual
GEM;Business As Usual;Reporting
GEM;Business Improvement
GEM;Business Improvement;Systems Admin;GSI Administration
GEM;Communication and Collaboration;Business As Usual;GPM
GEM;Communication and Collaboration;Grants Tool Kit
GEM;Data Management
GEM;Data Management;Business As Usual
GEM;Data Management;Systems Admin;Reporting
GEM;EGEM;GPM
GEM;GPM
GEM;GPM;Business As Usual
GEM;GPM;EGEM
GEM;GPM;EGEM;Data Management;Reporting;Governance and Change Control;Communication and Collaboration;Business Improvement
GEM;GPM;EGEM;GPS;Data Management
GEM;GPM;EGEM;Reporting;Analysis & Advice;Business Improvement;Governance and Change Control;Communication and Collaboration;Grants Tool Kit
GEM;GPM;EGEM;SAP;Reporting;Data Management;Systems Admin;Governance and Change Control;Project Planning;GSI Administration
GEM;GPM;Governance and Change Control;Business As Usual;Communication and Collaboration
GEM;GPM;Reporting;Systems Admin
GEM;GPM;Systems Admin
GEM;GPM;Training & Communications
GEM;GPS;GSI Administration;Data Model
GEM;Governance and Change Control;Communication and Collaboration;GSI Administration
GEM;Governance and Change Control;GSI Administration;Communication and Collaboration
GEM;Systems Admin
GEM;Systems Admin;Business As Usual
GEM;Training & Communications
GEM;Training Material
GEM;Training Material;Business As Usual;Training & Communications ;Communication and Collaboration;Professional Development
GPM
GPM;Analysis & Advice;Business Improvement
GPM;Business Improvement
GPM;Business Improvement;Communication and Collaboration;Systems Admin;Data Management
GPM;Business Improvement;Data Model;Process Map;Training & Communications
GPM;Business Improvement;Governance and Change Control
GPM;Business Improvement;Reporting
GPM;Data Management;Business Improvement;Communication and Collaboration;Systems Admin
GPM;Data Management;Reporting;GSI Administration;Systems Admin
GPM;GEM
GPM;GEM;EGEM;Altus;Training & Communications
GPM;GEM;EGEM;GPS;Reporting;Training Material;Systems Admin
GPM;GEM;EGEM;Systems Admin
GPM;Governance and Change Control;Systems Admin
GPM;Grants Tool Kit
GPM;Reporting
GPM;Reporting;Business As Usual
GPM;Reporting;Data Management;Analysis & Advice;Governance and Change Control;GPS;GEM;EGEM
GPM;Systems Admin
GPM;Systems Admin;Business Improvement
GPM;Systems Admin;Business Improvement;Communication and Collaboration;Data Model
GPM;Training & Communications
GPM;Training & Communications ;Data Model
GPM;Training Material
GPM;Training Material;Training & Communications
GPM;Training Material;Training & Communications ;Communication and Collaboration;Professional Development;Business As Usual
GPS;Business Improvement;Governance and Change Control;Data Management
GPS;Communication and Collaboration;Reporting
GPS;Data Management;Analysis & Advice;Training & Communications
GPS;Data Management;Reporting
GPS;Data Management;Systems Admin
GPS;Data Management;Systems Admin;Analysis & Advice
GPS;Data Request;Reporting;Grant Connect;GPM
GPS;EGEM;GPM;GEM;Governance and Change Control;Business Improvement;Data Management
GPS;GEM;GPM;EGEM;Communication and Collaboration;Data Model;Systems Admin
GPS;GEM;GPM;EGEM;Grant Connect;SAP;PDMS;Altus;Systems Admin;Governance and Change Control;Business Improvement
GPS;GEM;GPM;EGEM;Reporting;Training Material;Communication and Collaboration
GPS;GPM;EGEM;GEM;Reporting;Grant Connect;Data Management;Training & Communications
GPS;GPM;GEM;EGEM;Business Improvement;Data Model
GPS;GPM;GEM;EGEM;Reporting;Training Material;Business Improvement;Altus;Governance and Change Control;Systems Admin
GPS;GPM;Reporting
GPS;GPM;Reporting;Analysis & Advice;Business Improvement
GPS;GSI Administration;Governance and Change Control
GPS;Governance and Change Control;Communication and Collaboration
GPS;Reporting
GPS;Reporting;Analysis & Advice;GSI Administration
GPS;Reporting;Systems Admin;Data Management
GPS;Systems Admin;Data Management
GPS;Training & Communications
GSI Administration
GSI Administration;Business As Usual
GSI Administration;Business Improvement;Analysis & Advice;Reporting;Altus
GSI Administration;Business Improvement;Governance and Change Control;Project Planning
GSI Administration;Communication and Collaboration
GSI Administration;Communication and Collaboration;Governance and Change Control;Project Planning
GSI Administration;Communication and Collaboration;Governance and Change Control;SAP;Analysis & Advice
GSI Administration;Communication and Collaboration;Project Planning
GSI Administration;Data Management;Business Improvement;Process Map;Data Model;GPS
GSI Administration;Governance and Change Control
GSI Administration;Governance and Change Control;Systems Admin;Communication and Collaboration
GSI Administration;Reporting;Governance and Change Control
GSI Administration;SAP
GSI Administration;SAP;Business As Usual
GSI Administration;Systems Admin;GPM;GEM
Governance and Change Control
Governance and Change Control;Business As Usual
Governance and Change Control;Business As Usual;Communication and Collaboration
Governance and Change Control;Business Improvement
Governance and Change Control;Communication and Collaboration
Governance and Change Control;Communication and Collaboration;Business Improvement;Systems Admin;Data Model
Governance and Change Control;Communication and Collaboration;GSI Administration
Governance and Change Control;Communication and Collaboration;Reporting;Project Planning
Governance and Change Control;Data Management;Business Improvement;Reporting
Governance and Change Control;GEM;Systems Admin;Grants Tool Kit
Governance and Change Control;GSI Administration
Governance and Change Control;Grant Connect;Data Management
Governance and Change Control;Process Map;Project Planning;GSI Administration
Governance and Change Control;Professional Development
Governance and Change Control;Project Planning;Business Improvement;Data Model;Communication and Collaboration
Governance and Change Control;Project Planning;Systems Admin
Governance and Change Control;Reporting
Governance and Change Control;Reporting;Process Map;Business Improvement
Governance and Change Control;Systems Admin
Governance and Change Control;Training & Communications ;Business As Usual
Governance and Change Control;Training & Communications ;Grants Tool Kit;Business Improvement
Grant Connect
Grant Connect;Analysis & Advice;Reporting;Communication and Collaboration
Grant Connect;Data Management;Reporting;Systems Admin
Grant Connect;GPM
Grant Connect;PDMS;Analysis & Advice;Governance and Change Control;Business As Usual
Grants Tool Kit
Grants Tool Kit;Business Improvement;Training Material;Reporting
Grants Tool Kit;Communication and Collaboration
Grants Tool Kit;Process Map;GPM
Grants Tool Kit;Reporting
Grants Tool Kit;Reporting;Training Material
Grants Tool Kit;Training Material
Grants Tool Kit;Training Material;Business As Usual
PDMS;Reporting
PDMS;Reporting;Business As Usual
Process Map
Process Map;Business Improvement
Process Map;Business Improvement;Communication and Collaboration
Process Map;Governance and Change Control
Process Map;Grants Tool Kit
Professional Development
Professional Development;Business As Usual
Professional Development;Business As Usual;Training & Communications
Professional Development;Training Material;Grants Tool Kit
Project Planning
Project Planning;Communication and Collaboration
Project Planning;Communication and Collaboration;Governance and Change Control;Business Improvement
Project Planning;GSI Administration
Project Planning;Governance and Change Control;Business Improvement
Project Planning;Reporting;Business As Usual
Reporting
Reporting;Altus;Governance and Change Control;Business As Usual
Reporting;Altus;Governance and Change Control;GSI Administration
Reporting;Analysis & Advice
Reporting;Analysis & Advice;Data Model
Reporting;Analysis & Advice;Governance and Change Control
Reporting;Business As Usual
Reporting;Business As Usual;Communication and Collaboration
Reporting;Business As Usual;Project Planning
Reporting;Business Improvement
Reporting;Business Improvement;Data Management
Reporting;Business Improvement;Data Model;Grants Tool Kit;Analysis & Advice
Reporting;Business Improvement;Governance and Change Control
Reporting;Communication and Collaboration
Reporting;Communication and Collaboration;Business As Usual
Reporting;Communication and Collaboration;Governance and Change Control;Project Planning;Business Improvement
Reporting;Communication and Collaboration;Grants Tool Kit;Analysis & Advice;Business As Usual
Reporting;Data Management
Reporting;Data Management;Business As Usual
Reporting;Data Management;Business Improvement
Reporting;Data Management;GPM;Business As Usual
Reporting;Data Request;GSI Administration
Reporting;Data Request;Governance and Change Control
Reporting;GPM;Business As Usual;EGEM
Reporting;GPS;Analysis & Advice;Data Request;Business As Usual
Reporting;GPS;GPM;EGEM;GEM;Business As Usual
Reporting;GPS;Systems Admin
Reporting;GSI Administration;Business Improvement
Reporting;GSI Administration;Grants Tool Kit
Reporting;Governance and Change Control
Reporting;Governance and Change Control;Analysis & Advice;Business As Usual
Reporting;Governance and Change Control;Business As Usual
Reporting;Governance and Change Control;Business As Usual;Training & Communications
Reporting;Governance and Change Control;Business Improvement
Reporting;Governance and Change Control;Communication and Collaboration
Reporting;Governance and Change Control;Communication and Collaboration;Business Improvement
Reporting;Governance and Change Control;Grants Tool Kit
Reporting;Governance and Change Control;Process Map;Business Improvement
Reporting;Grant Connect
Reporting;PDMS
Reporting;PDMS;Business As Usual;Analysis & Advice
Reporting;Process Map;Business Improvement
Reporting;Project Planning;Business As Usual;Altus
Reporting;Project Planning;Governance and Change Control
Reporting;SAP;Business As Usual
Reporting;Systems Admin
Reporting;Training Material
Reporting;Training Material;Systems Admin;Professional Development
SAP
SAP;Altus;GSI Administration
SAP;Business As Usual
SAP;GSI Administration;Business As Usual
SAP;Reporting;Analysis & Advice;GSI Administration;Business As Usual
SAP;Reporting;Data Management
SAP;Reporting;Data Management;Business Improvement
Systems Admin
Systems Admin;Business Improvement;Governance and Change Control;Communication and Collaboration
Systems Admin;EGEM
Systems Admin;GEM
Systems Admin;GSI Administration
Training & Communications
Training & Communications ;Business As Usual;Systems Admin;EGEM
Training & Communications ;Business Improvement
Training & Communications ;Business Improvement;Project Planning;Governance and Change Control
Training & Communications ;Communication and Collaboration
Training & Communications ;Communication and Collaboration;EGEM;Business As Usual
Training & Communications ;Data Management
Training & Communications ;GEM;Reporting;Business As Usual
Training & Communications ;GSI Administration
Training & Communications ;GSI Administration;Grants Tool Kit;Business Improvement
Training & Communications ;Governance and Change Control;Grants Tool Kit;Data Management
Training & Communications ;Grants Tool Kit;Reporting
Training & Communications ;Reporting
Training & Communications ;Reporting;Business Improvement
Training & Communications ;Reporting;Business Improvement;Grants Tool Kit;Governance and Change Control
Training & Communications ;Reporting;Data Management;Business Improvement
Training & Communications ;Reporting;GPS;GPM;Grant Connect;Business As Usual
Training & Communications ;Reporting;Grants Tool Kit
Training & Communications ;Reporting;Training Material
Training Material
Training Material;Business As Usual;GSI Administration
Training Material;GSI Administration
Training Material;Grants Tool Kit
Training Material;Reporting
Training Material;Training & Communications